## Enhancement Roadmap
DeepMindQ — 45 Core Engine Enhancements
# | ID | Engine | Enhancement | Description | Priority | Impact | Effort | Category
Email Engine
1 | E-01 | Email Engine | SMTP Provider Integration | Integrate a real email sending provider (Resend, SendGrid, Amazon SES, or Postmark) with API key configuration in settings. The queue has status tracking but zero sending logic. | Critical | High | Medium | Sending
2 | E-02 | Email Engine | Queue PATCH Endpoint | The queue screen calls PATCH /api/queue with {action: 'pause'¦'resume'} but only a GET handler exists. Add PATCH for pause/resume/retry/cancel actions. | Critical | High | Low | Queue
3 | E-03 | Email Engine | Email Sending Cron Worker | Implement a background cron or webhook-based worker that processes the SendQueue: picks pending items, calls the SMTP provider, updates status to sent/failed, handles retries with exponential backoff. | Critical | High | Medium | Sending
4 | E-04 | Email Engine | Retry Logic with Exponential Backoff | SendQueue has retryCount field but it's never incremented. On failure, retry up to 3 times with delays of 5min, 30min, 2hr. Mark as permanently failed after max retries. | High | Medium | Low | Queue
5 | E-05 | Email Engine | Email Scheduling System | Add date/time picker UI for scheduling emails. Store scheduledAt properly. The cron worker should respect scheduling and only send when scheduledAt <= now. | High | Medium | Medium | Queue
6 | E-06 | Email Engine | Email Thread Tracking | Add In-Reply-To and References headers for conversation threading. Track Message-ID in the Draft model. When a reply comes in, link it to the original draft. | Medium | Medium | Medium | Reply Mgmt
7 | E-07 | Email Engine | Inbound Email Webhook (Replies) | Create a webhook endpoint (POST /api/webhooks/reply) that receives parsed reply emails (via SendGrid inbound, Resend inbound, or custom MX). Auto-categorize replies (positive, negative, OOO, unsubscribe). | Critical | High | Medium | Reply Mgmt
8 | E-08 | Email Engine | Bounce Webhook Handler | Create POST /api/webhooks/bounce to receive bounce notifications from the email provider. Auto-classify as hard/soft bounce, update contact status, add to suppression list for hard bounces. | High | High | Low | Deliverability
9 | E-09 | Email Engine | Unsubscribe Link & Compliance | Auto-append an unsubscribe link to every outbound email. Create a GET /api/unsubscribe endpoint. Track consent status. Add List-Unsubscribe header. GDPR/CAN-SPAM compliant. | Critical | High | Low | Compliance
10 | E-10 | Email Engine | A/B Testing for Subject Lines | Generate 2-3 subject line variants per email using AI. Randomly assign to leads. Track open rates per variant. Declare a winner after N sends. | Medium | High | High | Optimization
11 | E-11 | Email Engine | Email Open & Click Tracking | Embed a 1x1 tracking pixel for opens. Rewrite links with tracking redirects for clicks. Store events in a new EmailEvent model. Show open/click rates in analytics. | Medium | High | Medium | Analytics
12 | E-12 | Email Engine | Bulk Draft Operations | Add bulk approve, reject, regenerate, and delete actions to the drafts screen. Support selecting multiple drafts via checkboxes and applying actions in batch. | High | Medium | Low | UX
13 | E-13 | Email Engine | Deduplicate Generation Code | Three copies of email generation logic exist: email-generation.ts, drafts/route.ts, ai/generate/route.ts. Consolidate into a single source of truth. Remove hardcoded ZAI_CONFIG credentials. | High | Medium | Medium | Code Quality
14 | E-14 | Email Engine | Email Template System | Create a template library with editable subject/body patterns per service line. Support variable placeholders like {{name}}, {{company}}, {{pain_point}}. Let users create custom templates. | High | Medium | Medium | Generation
15 | E-15 | Email Engine | Multi-Step Email Sequences | Design drip campaign support: Sequence = ordered list of emails with delays (e.g., Day 0: intro, Day 3: case study, Day 7: CTA). Track which step each contact is on. | Medium | High | High | Campaigns
Capability Engine
16 | C-01 | Capability Engine | True Semantic Search with Embeddings | Replace Jaccard similarity (which is just token overlap) with real transformer-based embeddings. Use OpenAI embeddings, Cohere, or a local model. Store vectors in a vector DB (pgvector, Pinecone, Qdrant). | Critical | High | High | Search
17 | C-02 | Capability Engine | Vector Database Integration | Add a vector store for capability assets. Generate embeddings on asset create/update. Perform approximate nearest neighbor (ANN) search. This is essential for RAG quality at scale. | Critical | High | High | Search
18 | C-03 | Capability Engine | Add targetCompanySizes to Schema | The search code reads cap.targetCompanySizes but the Prisma schema doesn't have this column. Add it as a String field (JSON array stored as string) so company size filtering actually works. | Critical | Medium | Low | Schema
19 | C-04 | Capability Engine | Robust PDF Parsing | Replace regex-based PDF text extraction (Tj/TJ operators) with a proper library like pdf-parse or pdfjs-dist. The current approach fails on most modern PDFs (compressed streams, encrypted). | High | High | Low | Ingestion
20 | C-05 | Capability Engine | Robust DOCX Parsing | Replace regex-based <w:t> tag parsing with the mammoth.js or docx4js library. Current approach fails on complex formatting, tables, headers/footers, and nested elements. | High | Medium | Low | Ingestion
21 | C-06 | Capability Engine | Document Deduplication | Hash extracted text (or use AI similarity) to detect duplicate uploads. Show warning before creating duplicate assets. Option to merge or replace existing assets. | High | Medium | Medium | Ingestion
22 | C-07 | Capability Engine | Asset Versioning System | The schema has a version field but the PUT endpoint never increments it. Add version tracking: auto-increment on edit, store previous versions, allow viewing/restoring history. | Medium | Medium | Low | CRUD
23 | C-08 | Capability Engine | Asset Relationships & Linking | Create explicit relationships between assets (e.g., a case_study links to its parent service_line, proof_points link to their case_study). Add parentAssetId or a junction table. | High | Medium | Medium | Data Model
24 | C-09 | Capability Engine | Search Result Feedback Loop | Add thumbs up/down on search results. Track which results were used in email generation. Use this signal to boost/reduce asset relevance scores over time. | Medium | High | Medium | Search
25 | C-10 | Capability Engine | Knowledge Base Export/Import | Add export to JSON/CSV and import from structured data. Users should be able to backup, share, and migrate their knowledge base between instances. | Medium | Medium | Low | Data Mgmt
26 | C-11 | Capability Engine | Bulk Asset Operations | Add bulk create, edit, delete, activate/deactivate for capability assets. Support CSV upload of structured knowledge data (not just documents). | High | Medium | Low | UX
27 | C-12 | Capability Engine | Auto-Enrichment from Website | Scrape the company's own website (services pages, case studies, about page) and auto-generate capability assets. Use LLM to extract structured knowledge from web content. | Medium | High | High | Ingestion
28 | C-13 | Capability Engine | Knowledge Coverage Scoring Dashboard | Enhance the coverage analysis to show a real-time score per industry, role, and service line. Visualize gaps as a heat map. Trigger alerts when coverage drops below thresholds. | Medium | Medium | Medium | Analytics
29 | C-14 | Capability Engine | Multi-File Upload | Allow uploading multiple documents at once (drag 5 PDFs). Process them in parallel. Show progress per file. Aggregate all extracted assets into the knowledge base. | Medium | Medium | Medium | UX
30 | C-15 | Capability Engine | Asset Tagging System | Add free-form tags to assets beyond the structured fields. Allow filtering and searching by tags. Support tag auto-suggestion based on existing tags. | Low | Low | Low | UX
Lead Engine
31 | L-01 | Lead Engine | Unified Data Source (DB + Static) | CRITICAL BUG FIXED: /api/leads was reading only from static JSON files while uploaded leads went to the DB. Now unified to auto-detect and serve from DB when available. Enhance with seamless merging. | Critical | High | Done | Architecture
32 | L-02 | Lead Engine | Advanced Lead Scoring Model | Current scoring is basic (role + email health + data completeness). Add: company fit score (industry match, size match), engagement score (opens, clicks, replies), recency decay, and AI-predicted conversion probability. | High | High | Medium | Scoring
33 | L-03 | Lead Engine | Company Data Enrichment | Integrate enrichment APIs (Clearbit, Apollo, Hunter.io, LinkedIn) to auto-populate: company size, revenue, tech stack, funding, employee count, social profiles. Store in CompanyResearchCard. | High | High | Medium | Enrichment
34 | L-04 | Lead Engine | Lead Segmentation & Smart Lists | Create dynamic segments based on criteria (industry, score range, status, location, engagement). Save segments for reuse. Show segment counts. Use segments as targeting for email campaigns. | High | High | Medium | Segmentation
35 | L-05 | Lead Engine | Lead Export to CSV/Excel | Add export button that downloads filtered leads as CSV or XLSX with all available fields. Include export options for selected leads only or entire filtered set. | High | Medium | Low | Data Mgmt
36 | L-06 | Lead Engine | Lead Deduplication & Merge UI | Add a duplicate detection view that shows potential duplicates (fuzzy name + email matching). Allow manual merge: pick primary, keep best fields, archive duplicates. | High | Medium | Medium | Data Quality
37 | L-07 | Lead Engine | Status Workflow Management | Implement the 10-state FSM (imported → cleaned → drafted → queued → sent → replied → bounced → suppressed → archived) with proper transitions, validation, and UI status badges. | High | Medium | Medium | Workflow
38 | L-08 | Lead Engine | Column Mapping Preview & Edit | Before import, show a preview table: detected column mappings, first 5 rows of data, let user edit/confirm mappings. Currently mapping is auto-detected with no user review. | High | Medium | Medium | Import
39 | L-09 | Lead Engine | Incremental Import & Delta Processing | For large files (>10k rows), process in background batches. Show real-time progress. Support resume on failure. Add import queue with priority. | Medium | Medium | High | Import
40 | L-10 | Lead Engine | Real-time Email Verification Queue | Currently verification is on-demand (single/bulk API). Add auto-verify on import with a background queue. Show verification progress. Flag unverifiable leads automatically. | Medium | Medium | Medium | Verification
41 | L-11 | Lead Engine | Lead Activity Timeline | Show a chronological timeline per lead: import date, verification result, drafts generated, emails sent, replies received, bounces, status changes. Single view of all activity. | Medium | Medium | Medium | UX
42 | L-12 | Lead Engine | GDPR Consent Tracking | Add proper consent fields: consent source (form, list purchase, manual), consent date, IP address, double opt-in support. Add consent status filter. Auto-suppress non-consented leads. | High | Medium | Medium | Compliance
43 | L-13 | Lead Engine | Lead Notes & Activity Logging | Add free-text notes per contact (CompanyNote exists but no ContactNote). Auto-log all actions (draft generated, email sent, status changed) to the AuditLog with full context. | Medium | Medium | Low | UX
44 | L-14 | Lead Engine | Smart Lead Assignment | For teams: assign leads to sales reps based on territory, industry expertise, or round-robin. Track ownership. Show rep performance per assigned lead. | Medium | Medium | High | Team Mgmt
45 | L-15 | Lead Engine | Lead Source Tracking | Track where each lead came from (LinkedIn, event, referral, cold list, inbound). Add source field to Contact. Analyze conversion rates by source in analytics. | Medium | Medium | Low | Analytics

## Priority Matrix
Priority Matrix — Engine Breakdown
Engine | Critical | High | Medium | Low | Total
Email Engine | 5 | 6 | 4 | 0 | 15
Capability Engine | 3 | 5 | 6 | 1 | 15
Lead Engine | 1 | 8 | 6 | 0 | 15
TOTAL | 9 | 19 | 16 | 1 | 45

## Quick Wins
Quick Wins — High Impact, Lower Effort
# | ID | Enhancement | Engine | Impact | Effort
1 | E-01 | SMTP Provider Integration | Email Engine | High | Medium
2 | E-02 | Queue PATCH Endpoint | Email Engine | High | Low
3 | E-03 | Email Sending Cron Worker | Email Engine | High | Medium
4 | E-07 | Inbound Email Webhook (Replies) | Email Engine | High | Medium
5 | E-08 | Bounce Webhook Handler | Email Engine | High | Low
6 | E-09 | Unsubscribe Link & Compliance | Email Engine | High | Low
7 | E-11 | Email Open & Click Tracking | Email Engine | High | Medium
8 | C-04 | Robust PDF Parsing | Capability Engine | High | Low
9 | C-09 | Search Result Feedback Loop | Capability Engine | High | Medium
10 | L-02 | Advanced Lead Scoring Model | Lead Engine | High | Medium
11 | L-03 | Company Data Enrichment | Lead Engine | High | Medium
12 | L-04 | Lead Segmentation & Smart Lists | Lead Engine | High | Medium

## Implementation Phases
Suggested Implementation Phases
Phase | ID | Enhancement | Engine
Phase 1: Critical Fixes (Week 1-2)
| E-01 | SMTP Provider Integration | Email Engine
| E-02 | Queue PATCH Endpoint | Email Engine
| E-07 | Inbound Email Webhook | Email Engine
| E-09 | Unsubscribe Link & Compliance | Email Engine
| C-01 | True Semantic Search with Embeddings | Capability Engine
| C-03 | Add targetCompanySizes to Schema | Capability Engine
| L-01 | Unified Data Source (Already Fixed) | Lead Engine
Phase 2: Core Features (Week 3-5)
| E-03 | Email Sending Cron Worker | Email Engine
| E-04 | Retry Logic with Backoff | Email Engine
| E-05 | Email Scheduling System | Email Engine
| E-08 | Bounce Webhook Handler | Email Engine
| E-12 | Bulk Draft Operations | Email Engine
| E-13 | Deduplicate Generation Code | Email Engine
| E-14 | Email Template System | Email Engine
| C-04 | Robust PDF Parsing | Capability Engine
| C-05 | Robust DOCX Parsing | Capability Engine
| C-08 | Asset Relationships & Linking | Capability Engine
| C-11 | Bulk Asset Operations | Capability Engine
| L-02 | Advanced Lead Scoring Model | Lead Engine
| L-03 | Company Data Enrichment | Lead Engine
| L-04 | Lead Segmentation & Smart Lists | Lead Engine
| L-05 | Lead Export to CSV/Excel | Lead Engine
| L-07 | Status Workflow Management | Lead Engine
| L-08 | Column Mapping Preview & Edit | Lead Engine
Phase 3: Optimization (Week 6-8)
| E-06 | Email Thread Tracking | Email Engine
| E-10 | A/B Testing for Subject Lines | Email Engine
| E-11 | Email Open & Click Tracking | Email Engine
| E-15 | Multi-Step Email Sequences | Email Engine
| C-02 | Vector Database Integration | Capability Engine
| C-06 | Document Deduplication | Capability Engine
| C-07 | Asset Versioning System | Capability Engine
| C-09 | Search Result Feedback Loop | Capability Engine
| C-10 | Knowledge Base Export/Import | Capability Engine
| C-12 | Auto-Enrichment from Website | Capability Engine
| C-13 | Knowledge Coverage Scoring Dashboard | Capability Engine
| C-14 | Multi-File Upload | Capability Engine
| L-06 | Lead Deduplication & Merge UI | Lead Engine
| L-09 | Incremental Import & Delta Processing | Lead Engine
| L-10 | Real-time Email Verification Queue | Lead Engine
| L-11 | Lead Activity Timeline | Lead Engine
| L-12 | GDPR Consent Tracking | Lead Engine
Phase 4: Scale & Polish (Week 9+)
| C-15 | Asset Tagging System | Capability Engine
| L-13 | Lead Notes & Activity Logging | Lead Engine
| L-14 | Smart Lead Assignment | Lead Engine
| L-15 | Lead Source Tracking | Lead Engine