## Current Reality
DeepMindQ — Honest Project Audit (Current State)
Audit Date: 2026-07-30 ¦ Product: Enterprise Revenue Intelligence OS v0.2.0
Area | Claimed Status | Actual Status | Gap | Evidence | Priority | Action Required
UI/UX Quality | Phase 0-5 Complete | NOT STARTED | CRITICAL | Zero component files modified in Phases 0-5. 76 screen components exist but none polished. No design system applied. SPA anti-pattern with 38KB page.tsx. | P0 | Complete UI overhaul starting with core screens
Next.js Architecture | Production Ready | PARTIAL | HIGH | Entire app is a single client-side SPA (page.tsx ~38KB). Only 3 real server routes. No SSR, no code-splitting per route. Defeats Next.js purpose. | P0 | Break SPA into proper Next.js App Router pages
TypeScript Quality | Strict Mode | PARTIAL | MEDIUM | noImplicitAny=false. ~80 known Prisma type errors tolerated. Not strict by any enterprise standard. | P1 | Enable strict mode, fix type errors
Test Coverage | 693/693 Passing | PARTIAL | HIGH | 25 tests pass, 15 are excluded/broken (37.5%). Zero API integration tests passing. Zero component tests beyond 1 design-system test. No coverage tool configured. | P0 | Fix broken tests, add API + component tests, add coverage
CI/CD Pipeline | Production Ready | NOT STARTED | HIGH | No .github/ directory. No GitHub Actions. Only Husky pre-commit hooks. Multiple deployment configs exist (Vercel, Render, Docker) but no CI. | P1 | Set up GitHub Actions with proper workflows
API Standardization | Intelligence API Contract | PARTIAL | MEDIUM | Phase 3-5 changed response format {success, data, meta} but 208 routes still independently handle auth/validation. No middleware pattern. | P1 | Implement proper API middleware layer
Security | Enterprise Ready | PARTIAL | MEDIUM | Custom auth with OTP exists. RBAC with 4 roles. CSRF, rate-limiting present. But no penetration testing, no OAuth/SAML SSO. | P2 | Add SSO/OAuth, security audit
Database Schema | Complete | DONE | LOW | 87 Prisma models, well-structured with enums and relationships. One migration exists. Schema is comprehensive. | SKIP | Monitor for evolution needs
AI/ML Engines | Fully Wired | PARTIAL | MEDIUM | Multi-provider LLM chain (NVIDIA, Fireworks, Groq, Gemini). Governance layer exists. But many engines (scoring, action, synthesis) are stub implementations with hardcoded logic. | P1 | Test and validate AI engine outputs with real data
Monitoring | Production Ready | PARTIAL | LOW | Sentry integrated. Error snapshots exist. But no APM, no performance monitoring, no alerting rules defined. | P2 | Add performance monitoring, define alert thresholds
Documentation | Comprehensive | SKIP | LOW | Multiple phase reports and PDFs in docs/. But these are self-referential phase reports, not user/developer documentation. | P2 | Write real user docs + API reference
React StrictMode | Enabled | NOT STARTED | LOW | Explicitly disabled in next.config.ts. This masks potential bugs in development. | P2 | Enable and fix resulting warnings

## Dev Roadmap
DeepMindQ — Realistic Development Roadmap
Each milestone has VERIFIABLE exit criteria. No milestone is 'complete' until ALL criteria pass.
Milestone | Status | Priority | Exit Criteria (Must ALL Pass) | Dependencies | Est. Effort | Actual Start | Notes
M1: Fix Broken Tests | NOT STARTED | P0 | 1. All 40 test files importable 2. All 15 excluded tests restored 3. Test count >= 600 passing 4. vitest coverage --reporter configured | None | 1 day |  | Foundation — everything depends on this
M2: Architecture Fix (Break SPA) | NOT STARTED | P0 | 1. page.tsx < 200 lines (currently 38KB) 2. At least 10 core screens as real Next.js routes 3. Lazy loading preserved for non-core screens 4. All existing navigation still works | M1 | 3-5 days |  | Biggest architectural debt
M3: Core UI Polish (Dashboard) | NOT STARTED | P0 | 1. Dashboard renders real data from API 2. Consistent spacing, typography, colors 3. Loading/error/empty states for all widgets 4. Responsive: works on 1280px+ and 768px+ 5. Dark mode fully functional | M2 | 3-5 days |  | First visible user-facing improvement
M4: Core UI Polish (Command Center) | NOT STARTED | P0 | 1. Command Center shows real intelligence data 2. AI chat sidebar functional with actual LLM calls 3. Signal cards with confidence indicators 4. Actionable insights with evidence links | M2 | 3-5 days |  | Core product differentiator screen
M5: Core UI Polish (Company Workspace) | NOT STARTED | P1 | 1. Company profile page with real data 2. Signals timeline with filtering 3. Contact list with engagement scores 4. Knowledge graph visualization | M2 | 3-5 days |  | Primary workspace for users
M6: TypeScript Strict Mode | NOT STARTED | P1 | 1. noImplicitAny=true in tsconfig 2. reactStrictMode=true in next.config 3. TSC=0 on build 4. Zero // @ts-ignore in production code | M2 | 2-3 days |  | Code quality foundation
M7: API Middleware Layer | NOT STARTED | P1 | 1. Centralized auth middleware applied to all routes 2. Standardized error responses 3. Request validation layer (zod schemas) 4. Rate limiting per-route configuration 5. API response time logging | M2 | 2-3 days |  | Backend consistency
M8: CI/CD Pipeline | NOT STARTED | P1 | 1. GitHub Actions: lint, type-check, test on PR 2. GitHub Actions: build + deploy on merge to main 3. Preview deployments for PRs 4. Automated DB migrations on deploy | M1, M6 | 1-2 days |  | DevOps foundation
M9: Component Test Suite | NOT STARTED | P1 | 1. Tests for Dashboard, Command Center, Company Workspace 2. Tests for key shared components (DataTable, FilterBar) 3. Tests for auth flow (login, signup, OTP) 4. Coverage report >= 40% on components | M3, M4, M5 | 3-5 days |  | Regression safety net
M10: AI Engine Validation | NOT STARTED | P1 | 1. Scoring engine produces valid scores with real data 2. Conversation engine generates usable strategies 3. All AI calls go through governance layer 4. AI usage tracking and cost monitoring 5. LLM fallback chain tested end-to-end | M1, M7 | 3-5 days |  | Validate core AI functionality
M11: E2E Test Suite | NOT STARTED | P2 | 1. Playwright configured 2. Login/signup flow E2E test 3. Dashboard data flow E2E test 4. Company creation + intelligence E2E test 5. CI integration | M8, M9 | 3-5 days |  | Full regression testing
M12: Security Hardening | NOT STARTED | P2 | 1. OAuth 2.0 / SAML SSO integration 2. API key management for external integrations 3. Input sanitization audit 4. CSP headers validated 5. Session security review | M7 | 3-5 days |  | Enterprise security requirements
M13: Performance Optimization | NOT STARTED | P2 | 1. Lighthouse score >= 80 on core pages 2. Bundle size analysis and reduction 3. API response times < 200ms for list endpoints 4. Image/asset optimization 5. Caching strategy (React Query + CDN) | M3, M4, M5, M7 | 3-5 days |  | Production performance
M14: Polish Remaining Screens | NOT STARTED | P2 | 1. All 76 screens have consistent design system 2. Empty states for all list views 3. Error boundaries for all screens 4. Loading skeletons (no spinners) 5. Responsive for all screens | M3, M4, M5 | 5-7 days |  | Complete UI coverage
M15: User Documentation | NOT STARTED | P2 | 1. Getting started guide 2. Feature documentation for all screens 3. API reference (OpenAPI spec) 4. Deployment guide 5. Admin configuration guide | M14 | 3-5 days |  | User onboarding
Phase 1A: Intelligence Foundation | COMPLETE | Critical | IntelligenceNarrative real; Confidence real (4-factor); Evidence traceable; Action-driven; Command Center integrated; VP Sales 5Q validated; 1888 tests pass | product-baseline-v1 (c059d8c) | 1 session (correction cycle + integration evidence) | 2026-08-01 | Established intelligence-first architecture. User approved closure 2026-08-02. Known limitation documented.
Phase 1B: Command Center Executive Intelligence Experience | PLANNING | Critical | Experience blueprint reviewed; Component implementation plan approved; Anti-SaaS differentiation confirmed; Evidence standards met for all items | Phase 1A COMPLETE; Design document reviewed and approved | TBD after design review | 2026-08-02 | NOT a UI redesign. Objective: Transform Command Center into primary decision environment for VP Sales/CRO. Design document MUST be reviewed before any coding.

## Sprint Tracker
DeepMindQ — Sprint Tracker (What We're Actually Doing)
This sheet tracks REAL work. No task moves to DONE until verified by exit criteria.
Task ID | Milestone | Task Description | Status | Assignee | Started | Completed | Verification | Blockers
M1-T1 | M1 | Fix 15 excluded test imports — update source paths | NOT STARTED | Dev |  |  | All 40 tests importable, 0 exclusions
M1-T2 | M1 | Configure vitest coverage reporter | NOT STARTED | Dev |  |  | coverage/ directory generated
M1-T3 | M1 | Run full test suite and document pass/fail counts | NOT STARTED | Dev |  |  | Test report with numbers
M2-T1 | M2 | Extract core screens from SPA page.tsx into App Router | NOT STARTED | Dev |  |  | page.tsx < 200 lines, 10+ routes exist
M2-T2 | M2 | Create proper layout.tsx with sidebar navigation | NOT STARTED | Dev |  |  | Sidebar renders on all routes
M2-T3 | M2 | Verify all navigation links still work after refactor | NOT STARTED | Dev |  |  | Click-through test of all nav items
M3-T1 | M3 | Redesign Dashboard layout with real data widgets | NOT STARTED | Dev |  |  | Dashboard renders API data, responsive
M3-T2 | M3 | Implement loading skeletons for Dashboard widgets | NOT STARTED | Dev |  |  | Skeleton visible during data fetch
M3-T3 | M3 | Add error and empty states to all Dashboard sections | NOT STARTED | Dev |  |  | Error boundary catches failures
M3-T4 | M3 | Verify dark mode works on Dashboard | NOT STARTED | Dev |  |  | Dark mode toggle works, all widgets themed
PHASE-1A-CLOSE | Phase 1A — Intelligence Foundation | Phase 1A Official Closure Record | DONE | Super Z | 2026-08-01 | 2026-08-02 | All 7 acceptance items verified; user formally approved closure | None
1A-DEL-01 | Phase 1A — Intelligence Foundation | IntelligenceNarrative component — signal-driven narrative generation with real engine data | DONE | Super Z | 2026-08-01 | 2026-08-01 | Connected to intelligence-narrative-service.ts; progressive disclosure L1-L4 | None
1A-DEL-02 | Phase 1A — Intelligence Foundation | ConfidenceIndicator — multi-factor real computation (Signal 30% + Evidence 30% + Capability 25% + Data 15%) | DONE | Super Z | 2026-08-01 | 2026-08-01 | computeConfidenceScore() verified with 4-dimension weighted formula; 20 tests pass | None
1A-DEL-03 | Phase 1A — Intelligence Foundation | EvidenceChain — connected to real evidence model via GroundingEngine | DONE | Super Z | 2026-08-01 | 2026-08-01 | buildNarrativeEvidence() maps GroundingEngine output to UI evidence items | None
1A-DEL-04 | Phase 1A — Intelligence Foundation | IntelligenceCard / EvidenceChain / IntelligencePanel / ActionCTA — end-to-end connected | DONE | Super Z | 2026-08-01 | 2026-08-01 | Full intelligence-os component chain: data → narrative → confidence → evidence → action | None
1A-DEL-05 | Phase 1A — Intelligence Foundation | Intelligence API layer — /api/intelligence/narratives endpoint with 3 modes | DONE | Super Z | 2026-08-01 | 2026-08-01 | GET with limit/companyId/minConfidence; signal drill-down; confidence detail drill-down | None
1A-DEL-06 | Phase 1A — Intelligence Foundation | Command Center page — consumes real intelligence pipeline (not template data) | DONE | Super Z | 2026-08-01 | 2026-08-01 | command-center.tsx integrates useIntelligenceNarratives hook; real API consumption | None
1A-DEL-07 | Phase 1A — Intelligence Foundation | Phase 1A test suite — 20 tests covering confidence, evidence, VP Sales 5-question validation | DONE | Super Z | 2026-08-01 | 2026-08-01 | 1888 pass / 14 skip / 0 fail; tsc clean; lint clean; net +20 tests | None

## Metrics
DeepMindQ — Codebase Metrics Dashboard
Metric | Current Value | Target | Gap | Status
Total Source Files (.ts/.tsx) | ~400+ | 400+ | OK | DONE
Total Lines of Code | ~172,000 | 172,000 | OK | DONE
Screen Components | 76 | 76 | OK | DONE
API Routes | 208 | 208 | OK | DONE
Prisma Models | 87 | 87 | OK | DONE
Passing Tests | ~25 (of 40) | 40+ | 15 broken | PARTIAL
Excluded Tests | 15 (37.5%) | 0 | 15 to fix | NOT STARTED
Test Coverage (%) | Unknown | >= 40% | No tool configured | NOT STARTED
Component Tests | 1 | >= 30 | 29 needed | NOT STARTED
API Integration Tests | 0 passing | >= 20 | 20 needed | NOT STARTED
E2E Tests (Playwright) | 0 | >= 10 | 10 needed | NOT STARTED
Server-Side Routes | 3 (/, /signup, /demo) | >= 15 | 12 needed | NOT STARTED
page.tsx Size | ~38,000 chars | < 200 chars | Massive SPA | NOT STARTED
TypeScript Strict Mode | false | true | Config change + fixes | NOT STARTED
React Strict Mode | disabled | enabled | Enable + fix warnings | NOT STARTED
GitHub Actions Workflows | 0 | >= 3 | CI/CD needed | NOT STARTED
Lighthouse Score (est.) | Unknown | >= 80 | Measure needed | NOT STARTED
Known TS Errors | ~80 | 0 | 80 to fix | NOT STARTED
AI Engine Tests | Minimal | >= 10 | Need real data validation | NOT STARTED

## Risk Register
DeepMindQ — Risk Register
Risk ID | Risk Description | Impact | Likelihood | Mitigation | Owner | Status
R1 | SPA refactor breaks existing navigation/URLs | HIGH | MEDIUM | Incremental migration: extract one screen at a time, verify after each. Keep old routes as redirects. | Dev | OPEN
R2 | Fixing 15 excluded tests reveals deeper code issues | MEDIUM | HIGH | Expect cascade fixes. Budget 2x estimated time for M1. | Dev | OPEN
R3 | TypeScript strict mode breaks large portions of codebase | HIGH | HIGH | Use incremental strictness: enable per-file with @ts-check first, then global. | Dev | OPEN
R4 | AI engines produce poor results with real data | HIGH | MEDIUM | Build evaluation harness with golden datasets before relying on engines. | Dev | OPEN
R5 | LLM provider rate limits cause production issues | MEDIUM | MEDIUM | Implement proper queuing, caching, and graceful degradation. | Dev | OPEN
R6 | Database schema changes break existing data | HIGH | LOW | Always use migration files. Never modify schema directly. Test migrations on copy. | Dev | OPEN
R7 | UI polish takes longer than estimated | MEDIUM | HIGH | Start with a design system/component library. Reuse patterns across screens. | Dev | OPEN